## Sheet1
ML Project – Home Loan Credit
| Task | Timeline
1st Discussion
| EDA + Data Cleaning + Data Pre-proc | 11-25 Oct (19 to 26 Mid-term Break)
| Improvements (If any) based on feedback | 26-30 Oct
2nd Discussion
| Model Selection and performance | 30 Oct – 15 Nov
| Improvements (If any) based on feedback | 16 – 18 Nov
3rd + 4th Discussion
| Report | 19 – 27 Nov
| Improvements (If any) based on feedback | 28 Nov – 13 Dec